## Sheet 1
Name | Request Name | Request Id | Requester | Requested On | Request Start | Request Finish | Request Type | Request Status | Dispatcher | CP Priority | Department | Direction | Impact Cegeka (Y/N) | Impact employees | Impact GDPR (Y/N) | Impact on Agents | Impact on Customers | Impact Sopra (Y/N) | Internal work (in FTE) | IT internal DEV (MD) | Total IT Internal | Other mandays (Not IT) | IT Project Manager | Priority TO | Reference TO | Risk Bank | Validatiedatum budget | Validatiedatum business | Project Sponsor | Case Number
IMO-R5217 Integrate Insurance FOAg Proffess Loans | IMO-R5217 Integrate Insurance FOAg Proffess Loans | 0005217 | Melanie Parmentier | 2019-01-15 | 2021-01-01 | 2021-11-30 | Business Project with IT | HL to validate TO | Van Huizen Ruud | P0 - Critical |  | FRAP | N | Prévenir des changements |  | Ils vont travailler avec un nouvel outil | Aucun | No |  |  |  |  | WTU - Wim Tuts | P0 | ABACUS-Integration |  |  | 2021-11-22 | Bongaerts Anouk | FRAP-204
ICT-R5903 Improve Infrastructure Meeting Rooms | ICT-R5903 Improve Infrastructure Meeting Rooms | 0005903 | Niko De Mesmaker | 2019-12-24 | 2019-08-01 | 2020-03-31 | IT Project | Closed | Coolens Ann |  |  | ICT | [5 empty] | No |  |  |  |  | NDM - Niko De Mesmaker |  | ABACUS-Integration |  |  |  | Claeys Wim
ICT-R5945 General Activities before Closing Abacus | ICT-R5945 General Activities before Closing Abacus | 0005945 | Declerck Marc | 2020-01-20 |  |  | IT Project | Closed | Coolens Ann |  |  | ICT | [5 empty] | No |  |  |  |  | VME - Veerle Meesseman |  | ABACUS-Integration |  |  |  | Claeys Wim
IMO-R5946_Entry_Point_Agents | IMO-R5946_Entry_Point_Agents | 0005946 | Thomas Luk | 2020-01-20 |  |  | Business Project with IT | IT Analyse Estimation | Thomas Luk |  |  | IMO |  | nieuwe werkwijze |  | nieuwe werkwijze | geen | No |  |  |  |  | KTO - Koen Tourné |  | ABACUS-Integration |  |  |  | Bongaerts Anouk | FRAP-484 AB414
IMO-REP&BC-R6001- Activer-Lisser-Recup Cie -BGAAP | IMO-REP&BC-R6001- Activer-Lisser-Recup Cie -BGAAP | 0006001 | De Sart Yves | 2020-02-14 |  |  | Business Project with IT | Withdrawn | De Sart Yves |  |  | REP&BC |  | Yes |  | Yes | No | No |  |  |  |  | KWO - Katrijn Wolfs |  | ABACUS-Integration |  |  |  | Van Houtte Wouter | COF-288
IMO-R6013-DD for all type of credit payments | IMO-R6013-DD for all type of credit payments | 0006013 | Montjoie Juliette | 2020-02-21 | 2021-01-01 | 2022-03-31 | Business Project with IT | BC To Validate | Daise Lionel |  |  | CRED | N | En dehors de UL3, c'est la première fois que Crelan jouera le rôle DOM SEPA en tant que gestionnaire du mandat et émission des demandes de prélèvement. |  | Idem que pour client ==> informer les Agents AXA. | Pour le client AXA avec un compte mandaté AXA, le prélèvement partiel sera une nouveauté. En effet, Cadis prélève tant qu'il y a du disponible. Chose que la plateforme AXA ne fait pas systématiquement. | Yes |  | 100 |  |  | DTA - Dirk Taecke |  | ABACUS-Integration |  |  | 2022-03-21 | Vissers Patrick | Credit-498, 499, 500
IMO-R6033-ATSafe_integration_frontend | IMO-R6033-ATSafe_integration_frontend | 0006033 | Thomas Luk | 2020-03-05 |  |  | Business Project with IT | IT Analyse Estimation | Thomas Luk |  |  | IMO |  |  |  | 165 kantoren AXA maken gebruik van deze service | geen | Yes |  |  |  |  | IVB - Inge Van Der Bruggen |  | ABACUS-Integration |  |  |  | Bongaerts Anouk | FRAP-492 AB419
FRAP-R6035-appointmenttool_clients | FRAP-R6035-appointmenttool_clients | 0006035 | Thomas Luk | 2020-03-06 |  |  | Business Project with IT | Withdrawn | Thomas Luk |  |  | FRAP | [5 empty] | No | [6 empty] | ABACUS-Integration |  |  |  | Bongaerts Anouk
FRAP-R6038-Adapt_FrontEnd_client_RM | FRAP-R6038-Adapt_FrontEnd_client_RM | 0006038 | Thomas Luk | 2020-03-09 |  |  | Business Project with IT | IT Analyse Estimation | Thomas Luk | P1 - High |  | FRAP |  | efficiëntere werking |  | efficiëntere werking in kantoor, minder interventie in basisprocessen | de klant kan in de digitale kanalen de nodige aanpassingen doen zonder interventie van de kantoren | No |  |  |  |  | IVB - Inge Van Der Bruggen | P1 | ABACUS-Integration |  |  |  | Bongaerts Anouk
IMO-R6088-Abacus Clause vie privée Closing | IMO-R6088-Abacus Clause vie privée Closing | 0006088 | Debay Sylvie | 2020-04-29 |  |  | CR | CR To Analyse | Thomas Luk |  |  | IMO |  | Néant | No | Néant | Néant | Yes |  |  |  |  | MDB - Mike De Bruyn |  | ABACUS-Integration |  |  |  | Bongaerts Anouk | FRAP-606
IMO-R6089-Abacus Clause vie privée intégration | IMO-R6089-Abacus Clause vie privée intégration | 0006089 | Debay Sylvie | 2020-04-29 |  |  | CR | CR To Analyse | Corby Véronique |  |  | GECO |  | Néant | No | Néant | Néant | No |  |  |  |  | VME - Veerle Meesseman |  | ABACUS-Integration |  |  |  | Dieltiens Eugeen | FRAP-395
IMO-R6159-High Level SolStratMajor Abacus Projects | IMO-R6159-High Level SolStratMajor Abacus Projects | 0006159 | De Ville Filip | 2020-07-06 | 2020-07-12 | 2020-08-31 | Business Project with IT | Withdrawn | De Ville Filip |  |  | IMO | [5 empty] | Yes | [6 empty] | ABACUS-Integration |  |  |  | Voisin Philippe
IMO-R6163 TargetRetailJrnyProdOfferPricingDayBnk | IMO-R6163 TargetRetailJrnyProdOfferPricingDayBnk | 0006163 | De Ville Filip | 2020-07-07 | 2020-07-06 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 004
IMO-R6183 Design&Impl FronteOConsLoans | IMO-R6183 Design&Impl FronteOConsLoans | 0006183 | De Ville Filip | 2020-07-20 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | Bongaerts Anouk | Ab 055 frap-296
IMO-R6184 DesignImplemCoopSharesViaAXA | IMO-R6184 DesignImplemCoopSharesViaAXA | 0006184 | De Ville Filip | 2020-07-20 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 056
IMO-R6185 Mortgage Loans | IMO-R6185 Mortgage Loans | 0006185 | De Ville Filip | 2020-07-20 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | Bongaerts Anouk | Abacus 059
IMO-R6186 TargetRetailJrnyProdOfferPricingCred | IMO-R6186 TargetRetailJrnyProdOfferPricingCred | 0006186 | De Ville Filip | 2020-07-20 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 450
IMO-R6187 IntegrateInsuranceInFront-officeAgents | IMO-R6187 IntegrateInsuranceInFront-officeAgents | 0006187 | De Ville Filip | 2020-07-20 | 2020-07-07 | 2020-08-31 | Business Project with IT | Withdrawn | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2020-08-31 | De Ville Filip | Abacus 449
IMO-R6188 TargetRetailJrnyProdOfferPricingInvest | IMO-R6188 TargetRetailJrnyProdOfferPricingInvest | 0006188 | De Ville Filip | 2020-07-20 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 005
IMO-R6189Design&Implement commissioning Syst.xlsx | IMO-R6189Design&Implement commissioning Syst.xlsx | 0006189 | De Ville Filip | 2020-07-20 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 023
IMO-R6190 Credit_brokers_FrontEnd.xlsx | IMO-R6190 Credit_brokers_FrontEnd.xlsx | 0006190 | De Ville Filip | 2020-07-20 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | Bongaerts Anouk | Abacus 418
IMO-R6193 Implement new Crelan Mobile application | IMO-R6193 Implement new Crelan Mobile application | 0006193 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 388
IMO-R6194 myCrelan Gap analysis | IMO-R6194 myCrelan Gap analysis | 0006194 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 389
IMO-R6195 MigrDayBnkInvestDataAxaToCBS | IMO-R6195 MigrDayBnkInvestDataAxaToCBS | 0006195 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 052 en 284
IMO-R6196 Design&Implement bridges for cards.xlsx | IMO-R6196 Design&Implement bridges for cards.xlsx | 0006196 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 053
IMO-R6197 Design&ImplementBridge for Payments.xlsx | IMO-R6197 Design&ImplementBridge for Payments.xlsx | 0006197 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 273
IMO-R6199 Design & implement bridge for PSD2.xlsx | IMO-R6199 Design & implement bridge for PSD2.xlsx | 0006199 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 315
IMO-R6201 MigrateAllCustomerDataAXAtoKLDB | IMO-R6201 MigrateAllCustomerDataAXAtoKLDB | 0006201 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 111
IMO-R6202 Design&ImplArpsonOrSophis-OrOther.xlsx | IMO-R6202 Design&ImplArpsonOrSophis-OrOther.xlsx | 0006202 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 077
IMO-R6203 HQ Workstation | IMO-R6203 HQ Workstation | 0006203 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 301
IMO-R6204 InventoryOrganizeAxaHrInfo on Crelanet | IMO-R6204 InventoryOrganizeAxaHrInfo on Crelanet | 0006204 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 452
IMO-R6205 Uplift IT Infrastructure | IMO-R6205 Uplift IT Infrastructure | 0006205 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | ARU - Anita Rubbrecht | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 102
IMO-R6206 Design&ImplTgtBranchWorkstation.xlsx | IMO-R6206 Design&ImplTgtBranchWorkstation.xlsx | 0006206 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 298
IMO-R6207 IT License Consolidation | IMO-R6207 IT License Consolidation | 0006207 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 109
IMO-R6208 Migrate workplace data - agents | IMO-R6208 Migrate workplace data - agents | 0006208 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 440
IMO-R6209 ConstructionTargetLandscape IRB models | IMO-R6209 ConstructionTargetLandscape IRB models | 0006209 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 278
IMO-FIN-R6211-Load Reporting COREP AXA in DWH | IMO-FIN-R6211-Load Reporting COREP AXA in DWH | 0006211 | De Sart Yves | 2020-07-31 |  | 2020-12-31 | Business Project with IT | BC To Validate | Lekane Pascal |  |  | RIC | N | Yes Automatisation |  | No | No | No |  | 14 |  |  | KWO - Katrijn Wolfs |  | ABACUS-Integration |  |  | 2020-03-31 | Van Houtte Wouter | RISK-21 / Abacus 484
IMO-R6252-Optimise Bridge TPC to KLDB | IMO-R6252-Optimise Bridge TPC to KLDB | 0006252 | De Ville Filip | 2020-08-25 |  |  | IT Project | BUReq to validate IT | Verdickt Jo |  |  | ICT | N | #N/A |  | Sneller ter beschikking zijn van up-to-date klantendata in die applicaties die nog naar KLDB verwijzen voor deze data | #N/A | Yes |  | 45 |  |  | JOV - Jo Verdickt | P0 | ABACUS-Integration |  |  | 2021-03-18 | Fievez Anne
IMO-R6348-Customer Communication | IMO-R6348-Customer Communication | 0006348 | De Ville Filip | 2020-10-23 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 482
IMO-R6349-BringUniqueCoopValuesBrandingToNextLevel | IMO-R6349-BringUniqueCoopValuesBrandingToNextLevel | 0006349 | De Ville Filip | 2020-10-23 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 091
IMO-R6350-ImplDelAdvOfferForPersonalClients | IMO-R6350-ImplDelAdvOfferForPersonalClients | 0006350 | De Ville Filip | 2020-10-23 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 410
IMO-R6351-OptAssetAllocAlgorithmProcessPortfolios | IMO-R6351-OptAssetAllocAlgorithmProcessPortfolios | 0006351 | De Ville Filip | 2020-10-23 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 411
IMO-R6353-TargetRetailJrnyProdOfferPricingDayBnk | IMO-R6353-TargetRetailJrnyProdOfferPricingDayBnk | 0006353 | De Ville Filip | 2020-10-23 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 006
IMO-R6354-Execute AXA branch rebranding | IMO-R6354-Execute AXA branch rebranding | 0006354 | De Ville Filip | 2020-10-23 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 025
IMO-R6359-ATSafe integration front-end | IMO-R6359-ATSafe integration front-end | 0006359 | De Ville Filip | 2020-10-29 | 2020-10-01 | 2021-03-31 | Business Project with IT | Withdrawn | De Ville Filip |  |  | IMO | N |  |  |  |  | Yes |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 419
IMO-R6360-Entry Point Agents | IMO-R6360-Entry Point Agents | 0006360 | De Ville Filip | 2020-10-29 | 2020-10-01 | 2021-03-31 | Business Project with IT | Withdrawn | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | Bongaerts Anouk | Abacus 414
IMO-R6361-DesignImplement(C)GapsTarget FOCreopsPro | IMO-R6361-DesignImplement(C)GapsTarget FOCreopsPro | 0006361 | De Ville Filip | 2020-10-29 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 002
IMO-R6362-Design and implement new agent contracts | IMO-R6362-Design and implement new agent contracts | 0006362 | De Ville Filip | 2020-10-29 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 160
IMO-R6363-Harmonize agents mandates | IMO-R6363-Harmonize agents mandates | 0006363 | De Ville Filip | 2020-10-29 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 310
IMO-R6364-InvestigTactOptionForCutover(Org+Tech) | IMO-R6364-InvestigTactOptionForCutover(Org+Tech) | 0006364 | De Ville Filip | 2020-10-29 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 477
IMO-R6370-Extract Zoomit (transf serv & data mig) | IMO-R6370-Extract Zoomit (transf serv & data mig) | 0006370 | De Ville Filip | 2020-10-30 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 2991
IMO-R6371-AddLicenseFeeSopra(BudgetPlaceholder) | IMO-R6371-AddLicenseFeeSopra(BudgetPlaceholder) | 0006371 | De Ville Filip | 2020-10-30 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | MDC - Marc Declerck | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 480
IMO-R6374-DesignImplemCriticalGapsDayBnkCbsKyudoo | IMO-R6374-DesignImplemCriticalGapsDayBnkCbsKyudoo | 0006374 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | Yes |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 285
IMO-R6375-AXACreditPortfolioMgt-Opportunity Study | IMO-R6375-AXACreditPortfolioMgt-Opportunity Study | 0006375 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 455
IMO-R6376-Critical gaps target credits oper CADIS | IMO-R6376-Critical gaps target credits oper CADIS | 0006376 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 156
IMO-R6378-Design and implement bridge for OLTB | IMO-R6378-Design and implement bridge for OLTB | 0006378 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 316
IMO-R6379-Optimise Bridge TPC to KLDB | IMO-R6379-Optimise Bridge TPC to KLDB | 0006379 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Avacus 445
IMO-R6380-Design and implement bridge for 3DS | IMO-R6380-Design and implement bridge for 3DS | 0006380 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 317
IMO-R6382-Design and implement bridge for Payconiq | IMO-R6382-Design and implement bridge for Payconiq | 0006382 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 318
IMO-R6384-SetupCriticalGapsTargetInvestOPS | IMO-R6384-SetupCriticalGapsTargetInvestOPS | 0006384 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | Yes |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 042
IMO-R6386-AllowMeetingRequestsWithAgentsViaWebsite | IMO-R6386-AllowMeetingRequestsWithAgentsViaWebsite | 0006386 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 020
IMO-R6387-Replace Documentum by RFLOW + Workflow | IMO-R6387-Replace Documentum by RFLOW + Workflow | 0006387 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | Bongaerts Anouk | Abacus 434
IMO-R6388-Replace Quickfile by rFlow | IMO-R6388-Replace Quickfile by rFlow | 0006388 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 436
IMO-R6389-Reporting(ScopeSAP/BOand/orPowerBI) | IMO-R6389-Reporting(ScopeSAP/BOand/orPowerBI) | 0006389 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 481
IMO-R6391-Covered bonds | IMO-R6391-Covered bonds | 0006391 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | VME - Veerle Meesseman | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 268
IMO-R6392-FinancialMarketsFront2BackApp | IMO-R6392-FinancialMarketsFront2BackApp | 0006392 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 475
IMO-R6394-DataAvailabilityJointReporting | IMO-R6394-DataAvailabilityJointReporting | 0006394 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | [5 empty] | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  |  | De Ville Filip | Abacus 484
IMO-R6395-Automate commission treatment | IMO-R6395-Automate commission treatment | 0006395 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 439
IMO-R6396-AcctingTreatComCredFees&FairValValuation | IMO-R6396-AcctingTreatComCredFees&FairValValuation | 0006396 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip | P0 - Critical |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 438
IMO-R6397-RMBS srt vehicle in Luxembourg | IMO-R6397-RMBS srt vehicle in Luxembourg | 0006397 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 443
IMO-R6398-Financial Vehicles | IMO-R6398-Financial Vehicles | 0006398 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 442
IMO-R6399-Set-up common procurement capability | IMO-R6399-Set-up common procurement capability | 0006399 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 163
IMO-R6401-DesignImplemAddQrmRequirements | IMO-R6401-DesignImplemAddQrmRequirements | 0006401 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 229
IMO-R6403-CrelanToIssueT2-3EmissionsWithAXAVehicle | IMO-R6403-CrelanToIssueT2-3EmissionsWithAXAVehicle | 0006403 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 094
IMO-R6404-Placeholder budget Anaplan tool (SSO) | IMO-R6404-Placeholder budget Anaplan tool (SSO) | 0006404 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 185
IMO-R6405-Convert Euribor to Ester curve - Crelan | IMO-R6405-Convert Euribor to Ester curve - Crelan | 0006405 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 275
IMO-R6410-Set-up common xpofleet procurement cap | IMO-R6410-Set-up common xpofleet procurement cap | 0006410 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 458
IMO-R6411-Adapt DB Rate | IMO-R6411-Adapt DB Rate | 0006411 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 412
IMO-R6412-Valuation of loan portfolio fair value | IMO-R6412-Valuation of loan portfolio fair value | 0006412 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 454
IMO-R6416-Align job framework | IMO-R6416-Align job framework | 0006416 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 097
IMO-R6417-Extract ABB E-Docs Employee Personnel | IMO-R6417-Extract ABB E-Docs Employee Personnel | 0006417 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 4641
IMO-R6420-Harmonize status,rewards & benefits poli | IMO-R6420-Harmonize status,rewards & benefits poli | 0006420 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 472
IMO-R6421-Ensure scaling of appli & infrastructure | IMO-R6421-Ensure scaling of appli & infrastructure | 0006421 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | [5 empty] | No |  |  |  |  | FDV - Filip De Ville | P0 | ABACUS-Integration |  |  |  | De Ville Filip | Abacus 214
IMO-R6425-Connect Videoparlofonie to network Crela | IMO-R6425-Connect Videoparlofonie to network Crela | 0006425 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 421
IMO-R6426-IoT connectivity HQ | IMO-R6426-IoT connectivity HQ | 0006426 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 420
IMO-R6427-Connecting CCTV agency to network Crelan | IMO-R6427-Connecting CCTV agency to network Crelan | 0006427 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 428
IMO-R6428-Connect timelocks of agency network Crel | IMO-R6428-Connect timelocks of agency network Crel | 0006428 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 430
IMO-R6429-Connect walkietTalkies to network Crelan | IMO-R6429-Connect walkietTalkies to network Crelan | 0006429 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 426
IMO-R6430-IoT Connectivity Branch | IMO-R6430-IoT Connectivity Branch | 0006430 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 427
IMO-R6431-Connect Intrusion to network Crelan | IMO-R6431-Connect Intrusion to network Crelan | 0006431 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 423
IMO-R6432-Connect charging points to network Crela | IMO-R6432-Connect charging points to network Crela | 0006432 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 425
IMO-R6435-Security & data privacy for all projects | IMO-R6435-Security & data privacy for all projects | 0006435 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 489
IMO-R6436-ImproveSecurityMaturityIndexAboveLevel3 | IMO-R6436-ImproveSecurityMaturityIndexAboveLevel3 | 0006436 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 179
IMO-R6437-Improvement of Crelan Physical Security | IMO-R6437-Improvement of Crelan Physical Security | 0006437 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 463
IMO-R6441-MoveRegAddrAbbFromTrone2Anderlecht | IMO-R6441-MoveRegAddrAbbFromTrone2Anderlecht | 0006441 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | Abacus 263
IMO-R6442-Integration of DPO offices & processes | IMO-R6442-Integration of DPO offices & processes | 0006442 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip | ABACUS 476
IMO-RISK-R6480- Run SAS mensuel partie Retail | IMO-RISK-R6480- Run SAS mensuel partie Retail | 0006480 | Lekane Pascal | 2020-11-23 |  |  | CR | Closed | Lekane Pascal |  |  | RIC | N | Pas d'impact |  | Pas d'impact | Pas d'impact | No |  | 6 | 6 |  | KWO - Katrijn Wolfs |  | ABACUS-Integration |  |  | 2021-03-15 | Van Houtte Wouter | RISK-27
IMO-R6484 - Loan data reporting requirements | IMO-R6484 - Loan data reporting requirements | 0006484 | Tondeur Gilles | 2020-11-27 |  |  | Business Project with IT | PS To Validate TO | Tondeur Gilles |  |  | IMO | [5 empty] | No |  |  |  |  | KWO - Katrijn Wolfs |  | ABACUS-Integration |  |  |  | Van Houtte Wouter | one-pager IMO 484
FRAP-R6497-Kyudo_integrate_inventory_safes | FRAP-R6497-Kyudo_integrate_inventory_safes | 0006497 | Thomas Luk | 2020-12-07 |  |  | Business Project with IT | IT Analyse Estimation | Thomas Luk |  |  | FRAP |  |  |  | No wrong rental contracts | Correct rents will be charged | Yes |  |  |  |  | IVB - Inge Van Der Bruggen |  | ABACUS-Integration |  |  |  | Bongaerts Anouk | FRAP-572
ICT-R6597 Tobania Performance Testing | ICT-R6597 Tobania Performance Testing | 0006597 | De Ville Filip | 2021-02-17 |  |  | Business Project with IT | HL Validated | Coolens Ann |  |  | ICT | N |  |  | Make sure the performances remain optimal for UX. | Make sure the performances remain optimal for UX. | No |  |  |  |  | KTO - Koen Tourné |  | ABACUS-Integration |  |  | 2021-03-31 | De Ville Filip
IMO-R6926 Pricing & Scoring | IMO-R6926 Pricing & Scoring | 0006926 | De Ville Filip | 2022-01-14 |  |  | Business Project with IT | Open | De Ville Filip | P0 - Critical |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Integration |  |  |  | Bongaerts Anouk
IMO-R6931 Data Platform-foundation&building blocks | IMO-R6931 Data Platform-foundation&building blocks | 0006931 | De Ville Filip | 2022-01-18 |  |  | Business Project with IT | Open | De Ville Filip | P0 - Critical |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Integration |  |  |  | De Ville Filip
IMO-R6950 ContentAndCommunicationWebsite | IMO-R6950 ContentAndCommunicationWebsite | 0006950 | De Ville Filip | 2022-01-27 |  |  |  | Open | De Ville Filip | P0 - Critical |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Integration |  |  |  | De Ville Filip
IMO-R6954 LightCreditFlow for Brokers | IMO-R6954 LightCreditFlow for Brokers | 0006954 | De Ville Filip | 2022-01-30 |  |  | Business Project with IT | Open | De Ville Filip | P0 - Critical |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Integration |  |  |  | De Ville Filip | AB418
IMO-R6956 CommonIntegrLayer-Foundations&Tooling | IMO-R6956 CommonIntegrLayer-Foundations&Tooling | 0006956 | De Ville Filip | 2022-01-30 |  |  | Business Project with IT | Open | De Ville Filip | P0 - Critical |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Integration |  |  |  | De Ville Filip | AB055
IMO-R6957 Design LAN/WAN & Connectivity | IMO-R6957 Design LAN/WAN & Connectivity | 0006957 | De Ville Filip | 2022-01-30 |  |  | IT Project | Open | De Ville Filip | P0 - Critical |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Integration |  |  |  | De Ville Filip | AB102
IMO-R6972 Erase ABACUS Data&Apps Decommissioning | IMO-R6972 Erase ABACUS Data&Apps Decommissioning | 0006972 | De Ville Filip | 2022-02-08 |  |  | IT Project | Open | De Ville Filip | P1 - High |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Integration |  |  |  | De Ville Filip | Abacus 102
IMO-R6973 Execute performance test | IMO-R6973 Execute performance test | 0006973 | De Ville Filip | 2022-02-08 |  |  | IT Project | Active | De Ville Filip | P1 - High |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Integration |  |  |  | De Ville Filip | Abacus 102
IMO-R6974 RPA capability set up | IMO-R6974 RPA capability set up | 0006974 | De Ville Filip | 2022-02-08 |  |  | IT Project | Active | De Ville Filip | P1 - High |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Integration |  |  |  | De Ville Filip | Abacus 102
IMO-R6221-MigrateSuccessionDataAxaToCrelanSys | IMO-R6221-MigrateSuccessionDataAxaToCrelanSys | 0006221 | De Ville Filip | 2020-08-13 |  |  | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Migration |  |  | 2021-12-31 | De Ville Filip | Abacus 039
IMO-R6352-TargetRetailJrnyProdOfferPricingCredit | IMO-R6352-TargetRetailJrnyProdOfferPricingCredit | 0006352 | De Ville Filip | 2020-10-23 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 451
IMO-R6358-Migrate agent-branch-commission data | IMO-R6358-Migrate agent-branch-commission data | 0006358 | De Ville Filip | 2020-10-29 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 016
IMO-R6365-AXA Clients-Soft key option | IMO-R6365-AXA Clients-Soft key option | 0006365 | De Ville Filip | 2020-10-29 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 478bis
IMO-R6368-MigrateChannelsDataFromAxaToCrelan | IMO-R6368-MigrateChannelsDataFromAxaToCrelan | 0006368 | De Ville Filip | 2020-10-30 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 112
IMO-R6369-Migrate Zoomit (transf serv & data mig) | IMO-R6369-Migrate Zoomit (transf serv & data mig) | 0006369 | De Ville Filip | 2020-10-30 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 299
IMO-R6372-Migrate credit data from AXA to Crelan | IMO-R6372-Migrate credit data from AXA to Crelan | 0006372 | De Ville Filip | 2020-10-30 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 143
IMO-R6373-Domiciliation-Direct debit credit repaym | IMO-R6373-Domiciliation-Direct debit credit repaym | 0006373 | De Ville Filip | 2020-10-30 | 2020-10-01 | 2021-03-31 | Business Project with IT | Denied | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 444
IMO-R6377-MigrateContentieuxDataAXAToCrelanSystems | IMO-R6377-MigrateContentieuxDataAXAToCrelanSystems | 0006377 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 051
IMO-R6381-Migrate physically archived documents | IMO-R6381-Migrate physically archived documents | 0006381 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 313
IMO-R6383-MigrateDayBankInvestDataAXAtoCBS | IMO-R6383-MigrateDayBankInvestDataAXAtoCBS | 0006383 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | Yes |  |  |  |  | IHU - Isabelle Husson | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 284
IMO-R6385-AbbBranches&HQonCrlnet-ReplaceOnePlat | IMO-R6385-AbbBranches&HQonCrlnet-ReplaceOnePlat | 0006385 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 270
IMO-R6390-Migrate AXA documents to Rflow | IMO-R6390-Migrate AXA documents to Rflow | 0006390 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 437
IMO-R6400-Migrate AXA data to F2B tool | IMO-R6400-Migrate AXA data to F2B tool | 0006400 | De Ville Filip | 2020-11-02 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 474
IMO-R6402-Migrate data from Arpson to FIS | IMO-R6402-Migrate data from Arpson to FIS | 0006402 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 076
IMO-R6406-Migrate Accounting data | IMO-R6406-Migrate Accounting data | 0006406 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 073
IMO-R6413-MigrateHardHrPersnlDataToXtend&Payroll | IMO-R6413-MigrateHardHrPersnlDataToXtend&Payroll | 0006413 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 074
IMO-R6414-MigrateSoftHrPersonnelDataExclAcsRights | IMO-R6414-MigrateSoftHrPersonnelDataExclAcsRights | 0006414 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 453
IMO-R6418-MigrateABBElectronicEmplPersDocs | IMO-R6418-MigrateABBElectronicEmplPersDocs | 0006418 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 464
IMO-R6422-Call center infra for contact centers | IMO-R6422-Call center infra for contact centers | 0006422 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 298
IMO-R6423-Migration of Agency | IMO-R6423-Migration of Agency | 0006423 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 291
IMO-R6424-Connecting Accescontrol to network Crela | IMO-R6424-Connecting Accescontrol to network Crela | 0006424 | De Ville Filip | 2020-11-03 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 422
IMO-R6438-ComplianceAlignmentMethodo&DataMigration | IMO-R6438-ComplianceAlignmentMethodo&DataMigration | 0006438 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | BVG - Bart Van de Genachte | P0 | ABACUS-Migration |  |  | 2021-03-31 | De Ville Filip | Abacus 075
IMO-R6930 Overall migration program | IMO-R6930 Overall migration program | 0006930 | De Ville Filip | 2022-01-18 |  |  | Business Project with IT | Open | De Ville Filip | P0 - Critical |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Migration |  |  |  | De Ville Filip
IMO-R6953 ABB comm next to Crelan comm system | IMO-R6953 ABB comm next to Crelan comm system | 0006953 | De Ville Filip | 2022-01-30 |  |  | Business Project with IT | Open | De Ville Filip | P0 - Critical |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Migration |  |  |  | De Ville Filip | AB016
IMO-R6955 Migrate Procurement Transactions | IMO-R6955 Migrate Procurement Transactions | 0006955 | De Ville Filip | 2022-01-30 |  |  | Business Project with IT | Open | De Ville Filip | P0 - Critical |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Migration |  |  |  | De Ville Filip | AB074
IMO-R6958 Phone migration for HQ | IMO-R6958 Phone migration for HQ | 0006958 | De Ville Filip | 2022-01-30 |  |  | Business Project with IT | Open | De Ville Filip | P0 - Critical |  | IMO | [5 empty] | No | [6 empty] | ABACUS-Migration |  |  |  | De Ville Filip | AB298
IMO-R6192 Design&implTgtCustomerCareCenter.xlsx | IMO-R6192 Design&implTgtCustomerCareCenter.xlsx | 0006192 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | CVV - Christian Van Velthem | P0 | ABACUS-Orchestration |  |  | 2020-08-31 | De Ville Filip | Abacus 054
IMO-R6444-Testing Dry runs & waves | IMO-R6444-Testing Dry runs & waves | 0006444 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | [5 empty] | No |  |  |  |  | FDV - Filip De Ville | P0 | ABACUS-Orchestration |  |  |  | De Ville Filip | Abacus 486
IMO-R6445-Delivery assurance | IMO-R6445-Delivery assurance | 0006445 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | [5 empty] | No |  |  |  |  | FDV - Filip De Ville | P0 | ABACUS-Orchestration |  |  |  | De Ville Filip | Abacus 487
IMO-R6446-Program management (IMO) | IMO-R6446-Program management (IMO) | 0006446 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | [5 empty] | No |  |  |  |  | FDV - Filip De Ville | P0 | ABACUS-Orchestration |  |  |  | De Ville Filip | Abacus 485
IMO-R6447-Build&RunTrngProgForAgentsPreMigration | IMO-R6447-Build&RunTrngProgForAgentsPreMigration | 0006447 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Orchestration |  |  | 2021-03-31 | De Ville Filip | Abacus 019
IMO-R6448-Setup dynamic cultural journey for HQ | IMO-R6448-Setup dynamic cultural journey for HQ | 0006448 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Orchestration |  |  | 2021-03-31 | De Ville Filip | Abacus 465
IMO-R6449-Build and run training program in HQ | IMO-R6449-Build and run training program in HQ | 0006449 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Orchestration |  |  | 2021-03-31 | De Ville Filip | Abacus 188
IMO-R6450-Orchestrate impl new org & oper model | IMO-R6450-Orchestrate impl new org & oper model | 0006450 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Orchestration |  |  | 2021-03-31 | De Ville Filip | Abacus 098
IMO-R6451-Dfakto tool | IMO-R6451-Dfakto tool | 0006451 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | [5 empty] | No |  |  |  |  | FDV - Filip De Ville | P0 | ABACUS-Orchestration |  |  |  | De Ville Filip | Abacus 488
IMO-R6200 Design&ImplTgtCRM&AgentPortalCap.xlsx | IMO-R6200 Design&ImplTgtCRM&AgentPortalCap.xlsx | 0006200 | De Ville Filip | 2020-07-22 | 2020-07-07 | 2020-08-31 | Business Project with IT | IT Analyse Estimation | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Transformation |  |  | 2020-08-31 | De Ville Filip | Abacus 018
IMO-R6433-Prepare ECB AQR on consolidated entity | IMO-R6433-Prepare ECB AQR on consolidated entity | 0006433 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Upscale Risk & Compliance |  |  | 2021-03-31 | De Ville Filip | Abacus 279
IMO-R6434-ImplECB-NBBDemandsMoreITSecurityReq | IMO-R6434-ImplECB-NBBDemandsMoreITSecurityReq | 0006434 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Upscale Risk & Compliance |  |  | 2021-03-31 | De Ville Filip | Abacus 230
IMO-R6439-Prepare&Deliver redac ICAAP-ILAAP-Recove | IMO-R6439-Prepare&Deliver redac ICAAP-ILAAP-Recove | 0006439 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Upscale Risk & Compliance |  |  | 2021-03-31 | De Ville Filip | Abacus 307
IMO-R6440-Impl DPA maintenance Int. process steps | IMO-R6440-Impl DPA maintenance Int. process steps | 0006440 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project with IT | PS To Validate TO | De Ville Filip |  |  | IMO | N |  |  |  |  | No |  |  |  |  | KTO - Koen Tourné | P0 | ABACUS-Upscale Risk & Compliance |  |  | 2021-03-31 | De Ville Filip | Abacus 326
IMO-R6443-Implement risk appetite framework | IMO-R6443-Implement risk appetite framework | 0006443 | De Ville Filip | 2020-11-04 | 2020-10-01 | 2021-03-31 | Business Project without IT | HL to validate business | De Ville Filip |  |  | IMO | N |  |  |  |  | No | [5 empty] | P0 | ABACUS-Upscale Risk & Compliance |  |  | 2021-03-31 | De Ville Filip | Abacus 173
IMO-R6559-Asset Quality Review-DWH_tabel | IMO-R6559-Asset Quality Review-DWH_tabel | 0006559 | Stevens Joeri | 2021-01-15 |  |  | CR | Approved | Stevens Joeri |  |  | REP&BC |  | Departementen CRED REP&BC RIC | No | No | No | No |  |  | 25 |  | MRO - Marc Roels | P1 | ABACUS-Upscale Risk & Compliance |  |  |  | Van Houtte Wouter | MISALL-207
IMO - R6589 EBA SOT | IMO - R6589 EBA SOT | 0006589 | Sabbe Jean Louis | 2021-02-10 | 2021-02-10 | 2021-06-30 | Business Project with IT | Active | Sander Muylle |  |  | FIN | [5 empty] | No | [5 empty] | P0 | ABACUS-Upscale Risk & Compliance |  |  |  | Cnockaert Joris