## Sheet 1
Name | R-code project | Requests | Work ID # | Reference TO | Priority TO | CP Priority | Work Status | Work Type | Workflow | Project Health | IT Project Manager/Product Owner | Actual Start | Actual Finish | Baseline Start | Baseline Finish | Effort Actual-Roll Up | Effort Remain-Roll Up | Effort Required-Roll Up | Effort Reserved-Roll Up | Effort Total-Roll Up | Effort Variance - Roll Up | Approved MD IT | Baseline Effort-Roll Up | Baseline Required Effort-Roll Up | Baseline Reserved Effort-Roll Up | Slippage (d) | Release | Release Date | Show in IT-PMM (Y/N) | Show in STEERING (Y/N) | Schedule Start | Schedule Finish | Schedule Duration (d) | Schedule Variance (d) | Percent Complete | Late Start | Late Finish | Is there any personal data processing? | Impact Budget (Y/N) | Impact User (Y/N) | Labor Phase 1 | Labor Phase 2 | Labor Phase 3 | Labor CAP | Labor INT+EXT | Labor without Phase | Labor Total | Software | Hardware | Scope Health
Work: ICT-Abacus Architecture 2021 |  |  | 0007600 | ABACUS-Recurring |  | P1 - High | Requested | Recurring | Data Collection Other |  | RPE - Ronny Peleman | 2021-10-04 |  |  |  | 61.7 | 8.6 |  |  | 70.2 | [8 empty] | Yes | Yes | 2022-02-07 | 2022-03-11 | 25 |  | 93
Work: ICT-Abacus Architecture 2022 |  |  | 0007719 | ABACUS-Recurring |  | NP | Requested | Recurring | Data Collection Other |  | RPE - Ronny Peleman | 2022-01-12 |  |  |  | 13.4 | 21.4 |  |  | 34.8 | [8 empty] | Yes | Yes | 2022-02-07 | 2022-12-30 | 225 |  | 13
Work: ICT-R0001 Project demandIT IMO-budget |  |  | 0007576 | ABACUS-Recurring |  | NP | Temporary Future Project | IT Project | Data Collection IT Project |  | ACO - Ann Coolens | [14 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1 | [14 empty] | 194810
Work: ICT-ICT Projectwerk Abacus N-2 2021 |  |  | 0007354 | ABACUS-Recurring |  | P1 - High | Requested | Business Case Preparation | Data Collection Other |  | MDC - Marc Declerck | 2021-04-22 |  |  |  | 44 |  |  |  | 44 | [5 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-10 | 4 |  | 100
Work: IMO-R5217 BIA Migrate Professional loans to Creops | R5217 | 0005217 | 0007148 | ABACUS-Integration | P1 | P1 - High | Open/Baselined | Business Project with IT | Data Collection Business with IT | Orange | WTU - Wim Tuts | 2020-10-12 |  | 2020-10-12 | 2022-11-11 | 1095.4 | 511 | 162.4 |  | 1768.8 | -578.4 | 1300 | 1190.3 | 189 |  |  |  |  | Yes | Yes | 2022-02-07 | 2023-02-06 | 251 | -60 | 69 | [14 empty] | Green
Work: ICT-R5945 General Activities before Closing Abacus | R5945 | 0005945 | 0006909 | ABACUS-Recurring |  | P1 - High | Requested | IT Project | Data Collection IT Project | Green | VME - Veerle Meesseman | 2020-01-02 |  |  |  | 361.6 | 103.1 |  |  | 464.7 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-01-25 | 243 |  | 82 | [8 empty] | 27.5 | 322.1 | 349.6 | 349.6
Work: ICT-R5945 General Activities Abacus 2022 | R5945 | 0005945 | 0007762 | ABACUS-Recurring |  | P1 - High | Requested | IT Project | Data Collection IT Project |  | VME - Veerle Meesseman | 2022-01-24 |  |  |  | 4.7 | 45.3 |  |  | 50 | [8 empty] | Yes | Yes | 2022-02-07 | 2022-12-30 | 225 |  | 3
Work: IMO-R6013-DD for all type of credit payments | R6013 | 0006013 | 0007022 | ABACUS-Integration | P0 | P0 - Critical | Open/Baselined | Business Project with IT | Data Collection Business with IT | Green | DTA - Dirk Taecke | 2020-04-15 |  | 2020-04-15 | 2022-06-20 | 79.4 | 82.8 | 5 |  | 167.3 | -40.5 | 150 | 126.8 | 20 |  |  |  |  | Yes | Yes | 2022-02-07 | 2022-06-27 | 96 | -5 | 50 | [6 empty] | 15 |  | 15 |  |  | 15 |  |  | Green
Work: IMO-R6163 TargetRetailJrnyProdOfferPricingDayBnk | R6163 | 0006163 | 0007366 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT | Green | KTO - Koen Tourné | [6 empty] | 30 |  | 30 | [5 empty] | 229 |  |  | Yes | Yes | 2022-05-05 | 2024-04-29 | 499 | [16 empty] | Red
Work: IMO-R6183 Design&Impl FronteOConsLoans | R6183 | 0006183 | 0007303 | ABACUS-Integration | P0 | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | 2021-02-22 |  |  |  | 79.4 | 19.3 | 3336 |  | 3434.7 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-07-03 | 350 |  | 35 | [5 empty] | 4.4 |  |  | 0.6 | 3.8 |  | 4.4
Work: IMO-R6184 DesignImplemCoopSharesViaAXA | R6184 | 0006184 | 0007442 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 200 |  | 200 | [8 empty] | Yes | Yes | 2022-02-07 | 2022-04-05 | 42
Work: IMO-R6185 Mortgage Loans | R6185 | 0006185 | 0007379 | ABACUS-Integration | P0 | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | 2021-04-19 |  |  |  | 21.2 |  | 2333.3 |  | 2354.5 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-07-03 | 350 |  | 41 | [5 empty] | 8.8 |  |  | 1.4 | 7.4 |  | 8.8
Work: IMO-R6186 TargetRetailJrnyProdOfferPricingCred | R6186 | 0006186 | 0007380 | ABACUS-Integration | P0 | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [6 empty] | 75 |  | 75 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474
Work: IMO-R6188 TargetRetailJrnyProdOfferPricingInvest | R6188 | 0006188 | 0007396 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [17 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474
Work: IMO-R6189Design&Implement commissioning Syst.xlsx | R6189 | 0006189 | 0007410 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 656 |  | 656 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6190 Credit_brokers_FrontEnd.xlsx | R6190 | 0006190 | 0007418 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 685 |  | 685 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6193 Implement new Crelan Mobile application | R6193 | 0006193 | 0007230 | ABACUS-Integration | P0 | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | 2021-01-04 |  |  |  | 2.4 |  | 2554.6 |  | 2557 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-05-08 | 313 |  | 1 | [9 empty] | 2.4 | 2.4 | 2.4
Work: IMO-R6194 myCrelan Gap analysis | R6194 | 0006194 | 0007425 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 1055 |  | 1055 | [5 empty] | 527 |  |  | Yes | Yes | 2022-08-08 | 2023-08-07 | 250
Work: IMO-R6195 MigrDayBnkInvestDataAxaToCBS | R6195 | 0006195 | 0007427 | ABACUS-Integration | P0 | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [6 empty] | 3707 |  | 3707 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-07-14 | 359
Work: IMO-R6196 Design&Implement bridges for cards.xlsx | R6196 | 0006196 | 0007428 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [6 empty] | 220 |  | 220 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-07-14 | 359
Work: IMO-R6197 Design&ImplementBridge for Payments.xlsx | R6197 | 0006197 | 0007431 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [6 empty] | 200 |  | 200 | [8 empty] | Yes | Yes | 2022-02-07 | 2024-01-03 | 477
Work: IMO-R6199 Design & implement bridge for PSD2.xlsx | R6199 | 0006199 | 0007434 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [17 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6201 MigrateAllCustomerDataAXAtoKLDB | R6201 | 0006201 | 0007429 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [6 empty] | 960 |  | 960 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-04-21 | 303
Work: IMO-R6202 Design&ImplArpsonOrSophis-OrOther.xlsx | R6202 | 0006202 | 0007455 | ABACUS-Descoped | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 900 |  | 900 | [5 empty] | 482 |  |  | Yes | Yes | 2022-05-09 | 2023-06-02 | 266
Work: IMO-R6203 HQ Workstation | R6203 | 0006203 | 0007497 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [17 empty] | Yes | Yes | 2022-02-07 | 2024-01-03 | 477
Work: IMO-R6204 InventoryOrganizeAxaHrInfo on Crelanet | R6204 | 0006204 | 0007473 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project |  | JBL - Jan Blondeel | [17 empty] | Yes | Yes | 2022-02-07 | 2023-07-14 | 359
Work: IMO-R6205-Uplift IT infrastructure | R6205 | 0006205 | 0007488 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | ARU - Anita Rubbrecht | [17 empty] | Yes | Yes | 2022-02-07 | 2024-01-03 | 477
Work: IMO-R6205-1 Uplift IT infrastruct Setup datacenter | R6205-1 | 0006205 | 0007522 | ABACUS-Integration | P0 | P1 - High | Cancelled | IT Project | Data Collection IT Project |  | ARU - Anita Rubbrecht | [17 empty] | Yes | Yes
Work: IMO-R6205-11 Uplift IT infra Extract costs | R6205-11 | 0006205 | 0007532 | ABACUS-Integration | P0 | P1 - High | Requested | IT Project | Data Collection IT Project |  | ARU - Anita Rubbrecht | [17 empty] | Yes | Yes | 2022-02-07 | 2024-02-02 | 499
Work: IMO-R6205-2 Uplift IT infrastructure - Environment | R6205-2 | 0006205 | 0007523 | ABACUS-Integration | P0 | P1 - High | Requested | IT Project | Data Collection IT Project | Green | EBO - Emmanuel Bossier | 2021-06-28 |  |  |  | 18.1 | 24.3 | 502 |  | 544.4 | [8 empty] | Yes | Yes | 2022-02-07 | 2024-03-04 | 520 |  | 33 | [5 empty] | 3.1 |  |  |  | 3.1 |  | 3.1
Work: IMO-R6205-4 Uplift IT infra Branch migration | R6205-4 | 0006205 | 0007525 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | ARU - Anita Rubbrecht | [14 empty] | 589 |  |  | Yes | Yes | 2023-06-06 | 2023-11-03 | 106
Work: IMO-R6205-6 Uplift IT infra Abacus applicat decomm | R6205-6 | 0006205 | 0007527 | ABACUS-Integration | P0 | P1 - High | Requested | IT Project | Data Collection IT Project |  | ARU - Anita Rubbrecht | [17 empty] | Yes | Yes | 2022-02-07 | 2024-02-02 | 499
Work: IMO-R6205-7 Uplift IT infra AIX servers purchase | R6205-7 | 0006205 | 0007528 | ABACUS-Integration | P0 | P1 - High | Requested | IT Project | Data Collection IT Project |  | ARU - Anita Rubbrecht | [17 empty] | Yes | Yes | 2022-02-07 | 2024-01-03 | 477
Work: IMO-R6205-8 Uplift IT infrastructure Project Mngmt | R6205-8 | 0006205 | 0007529 | ABACUS-Integration | P0 | P1 - High | Requested | IT Project | Data Collection IT Project |  | ARU - Anita Rubbrecht | [17 empty] | Yes | Yes | 2022-02-07 | 2024-02-02 | 499
Work: IMO-R6205-9 Uplift IT infrastructure Infra | R6205-9 | 0006205 | 0007530 | ABACUS-Integration | P0 | P1 - High | Requested | IT Project | Data Collection IT Project |  | ARU - Anita Rubbrecht | [14 empty] | 630 |  |  | Yes | Yes | 2023-10-04 | 2024-01-03 | 63
Work: IMO-R6206 Design&ImplTgtBranchWorkstation.xlsx | R6206 | 0006206 | 0007489 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT |  |  | CVV - Christian Van Velthem | [17 empty] | Yes | Yes | 2023-06-06 | 2023-12-04 | 127
Work: IMO-R6207 IT License Consolidation | R6207 | 0006207 | 0007492 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 609 |  |  | Yes | Yes | 2023-06-06 | 2023-12-01 | 126
Work: IMO-R6208 Migrate workplace data - agents | R6208 | 0006208 | 0007498 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [17 empty] | Yes | Yes | 2022-02-07 | 2024-01-03 | 477
Work: IMO-R6209 ConstructionTargetLandscape IRB models | R6209 | 0006209 | 0007506 | ABACUS-Integration | P0 | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 3000 |  | 3000 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-09-22 | 407
Work: IMO-FIN-R6211-Load Reporting COREP AXA in DWH | R6211 | 0006211 | 0007184 | ABACUS-Descoped |  | NP | On Hold | Business Project with IT | Data Collection Business with IT | Green | KWO - Katrijn Wolfs | 2020-12-23 |  | 2020-12-23 | 2021-06-30 | 27 | 22.9 | 15 |  | 64.9 | 5.1 | 70 | 70 | 17 |  |  |  |  | Yes | Yes | 2022-02-07 | 2022-03-31 | 39 | -193 | 52 | [8 empty] | 12.6 | 12.6 | 25.2 | 25.2
Work: IMO-R6221-MigrateSuccessionDataAxaToCrelanSys | R6221 | 0006221 | 0007440 | ABACUS-Migration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [6 empty] | 128 |  | 128 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-08-11 | 378
Work: IMO-R6252-Optimise Bridge TPC to KLDB | R6252 | 0006252 | 0007204 | ABACUS-Integration |  | P1 - High | Requested | Business Project with IT | Data Collection IT Project |  | JOV - Jo Verdickt | 2020-12-07 |  |  |  | 11.7 | 30.3 | 308.3 |  | 350.4 | [8 empty] | No | No | 2022-02-07 | 2022-12-30 | 225 |  | 3 | [9 empty] | 11.3 | 11.3 | 11.3
Work: IMO-R6348-Customer Communication | R6348 | 0006348 | 0007395 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project | [16 empty] | 633 |  |  | Yes | Yes | 2023-07-06 | 2024-01-03 | 125
Work: IMO-R6349-BringUniqueCoopValuesBrandingToNextLevel | R6349 | 0006349 | 0007393 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project without IT | Data Collection Business Project | [19 empty] | Yes | Yes | 2022-02-07 | 2023-12-22 | 471
Work: IMO-R6350-ImplDelAdvOfferForPersonalClients | R6350 | 0006350 | 0007398 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 425 |  | 425 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474
Work: IMO-R6351-OptAssetAllocAlgorithmProcessPortfolios | R6351 | 0006351 | 0007399 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 50 |  | 50 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-02-10 | 255
Work: IMO-R6352-TargetRetailJrnyProdOfferPricingCredit | R6352 | 0006352 | 0007402 | ABACUS-Migration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT | [8 empty] | 80 |  | 80 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474
Work: IMO-R6353-TargetRetailJrnyProdOfferPricingDayBnk | R6353 | 0006353 | 0007401 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [17 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474
Work: IMO-R6354-Execute AXA branch rebranding | R6354 | 0006354 | 0007411 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project | [16 empty] | 633 |  |  | Yes | Yes | 2023-07-06 | 2024-01-03 | 125
Work: IMO-R6358-MigrationAgents&BranchesIdentityData | R6358 | 0006358 | 0007409 | ABACUS-Migration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 1005 |  | 1005 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-08-25 | 387
Work: IMO-R6359-ATSafe integration front-end | R6359 | 0006359 | 0007419 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 200 |  | 200 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-24 | 285
Work: IMO-R6360-Entry Point Agents | R6360 | 0006360 | 0007417 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 25 |  | 25 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6361-DesignImplement(C)GapsTarget FOCreopsPro | R6361 | 0006361 | 0007407 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 320 |  | 320 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6362-Design and implement new agent contracts | R6362 | 0006362 | 0007415 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project | [16 empty] | 628 |  |  | Yes | Yes | 2023-01-05 | 2023-12-27 | 244
Work: IMO-R6363-Harmonize agents mandates | R6363 | 0006363 | 0007416 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project |  | KTO - Koen Tourné | [17 empty] | Yes | Yes | 2022-02-07 | 2024-01-03 | 477
Work: IMO-R6364-InvestigTactOptionForCutover(Org+Tech) | R6364 | 0006364 | 0007421 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [17 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474
Work: IMO-R6368-MigrateChannelsDataFromAxaToCrelan | R6368 | 0006368 | 0007422 | ABACUS-Migration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 362 |  | 362 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-08-11 | 378
Work: IMO-R6369-Migrate Zoomit (transf serv & data mig) | R6369 | 0006369 | 0007423 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 55 |  | 55 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-08-11 | 378
Work: IMO-R6370-Extract Zoomit (transf serv & data mig) | R6370 | 0006370 | 0007424 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 55 |  | 55 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-01-27 | 245
Work: IMO-R6371-AddLicenseFeeSopra(BudgetPlaceholder) | R6371 | 0006371 | 0007439 | ABACUS-Integration | P0 | P0 - Critical | Requested | IT Project | Data Collection IT Project |  | MDC - Marc Declerck | [14 empty] | 446 |  |  | Yes | Yes | 2023-01-05 | 2023-04-05 | 65
Work: IMO-R6372-Migrate credit data from AXA to Crelan | R6372 | 0006372 | 0007382 | ABACUS-Migration | P0 | NP | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | 2021-04-19 |  |  |  | 44.6 | 8.8 | 2579.6 |  | 2633 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-05-08 | 313 |  | 33 | [5 empty] | 2.8 |  |  | 0.8 | 2 |  | 2.8
Work: IMO-R6374-DesignImplemCriticalGapsDayBnkCbsKyudoo | R6374 | 0006374 | 0007433 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [17 empty] | Yes | Yes | 2022-02-07 | 2024-01-03 | 477
Work: IMO-R6375-AXACreditPortfolioMgt-Opportunity Study | R6375 | 0006375 | 0007438 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [6 empty] | 811 |  | 811 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6376-Critical gaps target credits oper CADIS | R6376 | 0006376 | 0007430 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [5 empty] | 3 |  |  | 3 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-05-08 | 313
Work: IMO-R6377-MigrateContentieuxDataAXAToCrelanSystems | R6377 | 0006377 | 0007426 | ABACUS-Migration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [5 empty] | 2 | 374 |  | 376 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-07-14 | 359
Work: IMO-R6378-Design and implement bridge for OLTB | R6378 | 0006378 | 0007435 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [6 empty] | 200 |  | 200 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-12-15 | 466
Work: IMO-R6380-Design and implement bridge for 3DS | R6380 | 0006380 | 0007436 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [6 empty] | 75 |  | 75 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6381-Migrate physically archived documents | R6381 | 0006381 | 0007432 | ABACUS-Migration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 10 |  | 10 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-07-14 | 359
Work: IMO-R6382-Design and implement bridge for Payconiq | R6382 | 0006382 | 0007437 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [17 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6383-MigrateDayBankInvestDataAXAtoCBS | R6383 | 0006383 | 0007443 | ABACUS-Migration | P0 | P1 - High | Cancelled | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [17 empty] | Yes | Yes
Work: IMO-R6384-SetupCriticalGapsTargetInvestOPS | R6384 | 0006384 | 0007441 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | IHU - Isabelle Husson | [17 empty] | Yes | Yes | 2022-02-07 | 2022-12-05 | 207
Work: IMO-R6385-AbbBranches&HQonCrlnet-ReplaceOnePlat | R6385 | 0006385 | 0007446 | ABACUS-Migration | P0 | P2 - Medium | Requested | Business Project without IT | Data Collection Business Project |  | KTO - Koen Tourné | [17 empty] | Yes | Yes | 2022-02-07 | 2023-07-14 | 359
Work: IMO-R6386-AllowMeetingRequestsWithAgentsViaWebsite | R6386 | 0006386 | 0007444 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT | [8 empty] | 50 |  | 50 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474
Work: IMO-R6387-Replace Documentum by RFLOW + Workflow | R6387 | 0006387 | 0007448 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 1069 |  | 1069 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6388-Replace Quickfile by rFlow | R6388 | 0006388 | 0007449 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 690 |  | 690 | [8 empty] | Yes | Yes | 2022-02-07 | 2022-06-24 | 95
Work: IMO-R6389-Reporting(ScopeSAP/BOand/orPowerBI) | R6389 | 0006389 | 0007450 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 200 |  | 200 | [5 empty] | 492 |  |  | Yes | Yes | 2022-07-04 | 2023-06-16 | 239
Work: IMO-R6390-Migrate AXA documents to Rflow | R6390 | 0006390 | 0007447 | ABACUS-Migration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 300 |  | 300 | [5 empty] | 531 |  |  | Yes | Yes | 2022-04-20 | 2023-08-11 | 328
Work: IMO-R6391-Covered bonds | R6391 | 0006391 | 0007405 | ABACUS-Descoped | P0 | NP | Requested | Business Project with IT | Data Collection Business with IT |  | VME - Veerle Meesseman | 2021-05-10 |  |  |  | 24.2 | 9.5 | 3200.8 |  | 3234.5 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-02-07 | 252 |  | 45 | [9 empty] | 0.6 | 0.6 | 0.6
Work: IMO-R6392-FinancialMarketsFront2BackApp | R6392 | 0006392 | 0007468 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 200 |  | 200 | [8 empty] | Yes | Yes | 2022-02-07 | 2022-09-09 | 148
Work: IMO-R6394-DataAvailabilityJointReporting | R6394 | 0006394 | 0007469 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | 2021-07-07 |  |  |  | 9 | 4.5 |  |  | 13.5 | [8 empty] | Yes | Yes | 2022-02-07 | 2024-01-03 | 477 |  | 27
Work: IMO-R6395-Automate commission treatment | R6395 | 0006395 | 0007463 | ABACUS-Descoped | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 1376 |  | 1376 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6396-AcctingTreatComCredFees&FairValValuation | R6396 | 0006396 | 0007462 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [5 empty] | 2 | 1195 |  | 1197 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6397-RMBS srt vehicle in Luxembourg | R6397 | 0006397 | 0007465 | ABACUS-Descoped | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 800 |  | 800 | [5 empty] | 468 |  |  | Yes | Yes | 2022-03-07 | 2023-05-10 | 295
Work: IMO-R6398-Financial Vehicles | R6398 | 0006398 | 0007464 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 762 |  | 762 | [5 empty] | 468 |  |  | Yes | Yes | 2022-03-07 | 2023-05-10 | 295
Work: IMO-R6399-Set-up common procurement capability | R6399 | 0006399 | 0007457 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT | [19 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6400-Migrate AXA data to F2B tool | R6400 | 0006400 | 0007467 | ABACUS-Migration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 195 |  | 195 | [5 empty] | 619 |  |  | Yes | Yes | 2023-01-16 | 2023-12-15 | 231
Work: IMO-R6401-DesignImplemAddQrmRequirements | R6401 | 0006401 | 0007458 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 65 |  | 65 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6402-Migrate data from Arpson to FIS | R6402 | 0006402 | 0007452 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 195 |  | 195 | [5 empty] | 502 |  |  | Yes | Yes | 2022-08-01 | 2023-06-30 | 230
Work: IMO-R6403-CrelanToIssueT2-3EmissionsWithAXAVehicle | R6403 | 0006403 | 0007456 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 15 |  | 15 | [5 empty] | 550 |  |  | Yes | Yes | 2023-07-03 | 2023-09-08 | 48
Work: IMO-R6404-Placeholder budget Anaplan tool (SSO) | R6404 | 0006404 | 0007470 | ABACUS-Integration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [14 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-10 | 4
Work: IMO-R6405-Convert Euribor to Ester curve - Crelan | R6405 | 0006405 | 0007459 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 140 |  | 140 | [8 empty] | Yes | Yes | 2022-02-07 | 2022-05-25 | 76
Work: IMO-R6406-Migrate Accounting data | R6406 | 0006406 | 0007451 | ABACUS-Migration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | 2021-06-18 |  |  |  | 3 | 1.5 | 41 |  | 45.5 | [8 empty] | Yes | Yes | 2023-01-05 | 2023-12-27 | 244 |  | 21
Work: IMO-R6410-Set-up common xpofleet procurement cap | R6410 | 0006410 | 0007460 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT | [8 empty] | 30 |  | 30 | [8 empty] | Yes | Yes | 2022-02-07 | 2022-04-29 | 58
Work: IMO-R6411-Adapt DB Rate | R6411 | 0006411 | 0007461 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 34 |  | 34 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6412-Valuation of loan portfolio fair value | R6412 | 0006412 | 0007466 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT | [19 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6413-MigrateHardHrPersnlDataToXtend&Payroll | R6413 | 0006413 | 0007471 | ABACUS-Migration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 90 |  | 90 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-05-05 | 312
Work: IMO-R6414-MigrateSoftHrPersonnelDataExclAcsRights | R6414 | 0006414 | 0007474 | ABACUS-Migration | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 222 |  | 222 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-05-05 | 312
Work: IMO-R6416-Align job framework | R6416 | 0006416 | 0007472 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project | [19 empty] | Yes | Yes | 2022-02-07 | 2023-09-27 | 410
Work: IMO-R6417-Extract ABB E-Docs Employee Personnel | R6417 | 0006417 | 0007476 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 140 |  | 140 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-05-05 | 312
Work: IMO-R6418-MigrateABBElectronicEmplPersDocs | R6418 | 0006418 | 0007475 | ABACUS-Migration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 150 |  | 150 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-05-05 | 312
Work: IMO-R6420-Harmonize status,rewards & benefits poli | R6420 | 0006420 | 0007478 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project | [19 empty] | Yes | Yes | 2022-02-07 | 2023-05-05 | 312
Work: IMO-R6421-Ensure scaling of appli & infrastructure | R6421 | 0006421 | 0007494 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | FDV - Filip De Ville | [17 empty] | Yes | Yes | 2022-02-07 | 2023-06-30 | 349
Work: IMO-R6422-Call center infra for contact centers | R6422 | 0006422 | 0007496 | ABACUS-Migration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 630 |  |  | Yes | Yes | 2022-07-06 | 2024-01-03 | 375
Work: IMO-R6423-Migration of Agency | R6423 | 0006423 | 0007495 | ABACUS-Migration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [17 empty] | Yes | Yes | 2022-02-07 | 2024-01-03 | 477
Work: IMO-R6424-Connecting Accescontrol to network Crela | R6424 | 0006424 | 0007481 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 630 |  |  | Yes | Yes | 2023-09-06 | 2024-01-03 | 83
Work: IMO-R6425-Connect Videoparlofonie to network Crela | R6425 | 0006425 | 0007480 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 630 |  |  | Yes | Yes | 2023-09-06 | 2024-01-03 | 83
Work: IMO-R6426-IoT connectivity HQ | R6426 | 0006426 | 0007479 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 65 |  |  | Yes | Yes | 2023-09-06 | 2024-01-03 | 83
Work: IMO-R6427-Connecting CCTV agency to network Crelan | R6427 | 0006427 | 0007486 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 630 |  |  | Yes | Yes | 2023-08-14 | 2024-01-03 | 99
Work: IMO-R6428-Connect timelocks of agency network Crel | R6428 | 0006428 | 0007487 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 630 |  |  | Yes | Yes | 2023-08-07 | 2024-01-03 | 104
Work: IMO-R6429-Connect walkietTalkies to network Crelan | R6429 | 0006429 | 0007484 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 630 |  |  | Yes | Yes | 2023-09-06 | 2024-01-03 | 83
Work: IMO-R6430-IoT Connectivity Branch | R6430 | 0006430 | 0007485 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 630 |  |  | Yes | Yes | 2023-08-07 | 2024-01-03 | 104
Work: IMO-R6431-Connect Intrusion to network Crelan | R6431 | 0006431 | 0007482 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 630 |  |  | Yes | Yes | 2023-09-06 | 2024-01-03 | 83
Work: IMO-R6432-Connect charging points to network Crela | R6432 | 0006432 | 0007483 | ABACUS-Descoped | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | CVV - Christian Van Velthem | [14 empty] | 630 |  |  | Yes | Yes | 2023-09-06 | 2024-01-03 | 83
Work: IMO-R6433-Prepare ECB AQR on consolidated entity | R6433 | 0006433 | 0007507 | ABACUS-Upscale Risk & Compliance | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  |  | 2021-06-22 |  |  |  | 0.9 | 4.1 | 75 |  | 80 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-06-30 | 349 |  | 2
Work: IMO-R6434-ImplECB-NBBDemandsMoreITSecurityReq | R6434 | 0006434 | 0007504 | ABACUS-Upscale Risk & Compliance | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT | [8 empty] | 1375 |  | 1375 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474
Work: IMO-R6435-Security & data privacy for all projects | R6435 | 0006435 | 0007512 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT | [8 empty] | 1192.9 |  | 1192.9 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474 |  |  | 2022-02-25 | 2023-09-25
Work: IMO-R6436-ImproveSecurityMaturityIndexAboveLevel3 | R6436 | 0006436 | 0007503 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT | [8 empty] | 250 |  | 250 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474
Work: IMO-R6437-Improvement of Crelan Physical Security | R6437 | 0006437 | 0007510 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT | [8 empty] | 50 |  | 50 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-12-29 | 474
Work: IMO-R6438-ComplianceAlignmentMethodo&DataMigration | R6438 | 0006438 | 0007501 | ABACUS-Migration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | BVG - Bart Van de Genachte | [6 empty] | 250 |  | 250 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-08-11 | 378
Work: IMO-R6439-PrepAndDeliverRedacICAAP-ILAAP-Recovery | R6439 | 0006439 | 0007508 | ABACUS-Upscale Risk & Compliance | P0 | P2 - Medium | Requested | Business Project without IT | Data Collection Business Project | [19 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6440-ImplDpaMaintAppForEachIntProcessStep | R6440 | 0006440 | 0007509 | ABACUS-Upscale Risk & Compliance | P0 | P2 - Medium | Requested | Business Project with IT | Data Collection Business with IT |  | KTO - Koen Tourné | [17 empty] | Yes | Yes | 2022-02-07 | 2023-09-25 | 408
Work: IMO-R6441-MoveRegAddrAbbFromTrone2Anderlecht | R6441 | 0006441 | 0007505 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT | [19 empty] | Yes | Yes | 2022-02-07 | 2023-02-28 | 267
Work: IMO-R6442-Integration of DPO offices & processes | R6442 | 0006442 | 0007511 | ABACUS-Integration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT | [19 empty] | Yes | Yes | 2022-02-07 | 2023-04-06 | 294
Work: IMO-R6443-Implement risk appetite framework | R6443 | 0006443 | 0007502 | ABACUS-Upscale Risk & Compliance | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT | [19 empty] | Yes | Yes | 2022-02-07 | 2023-03-10 | 275
Work: IMO-R6444-Testing Dry runs & waves | R6444 | 0006444 | 0007518 | ABACUS-Orchestration | P0 | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT |  | FDV - Filip De Ville | [6 empty] | 4325.1 |  | 4325.1 | [8 empty] | Yes | Yes | 2022-02-07 | 2023-09-29 | 412
Work: IMO-R6445-Delivery assurance | R6445 | 0006445 | 0007519 | ABACUS-Orchestration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project |  | FDV - Filip De Ville | [14 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6446-Program management (IMO) | R6446 | 0006446 | 0007499 | ABACUS-Orchestration | P0 | P0 - Critical | Requested | Business Project without IT | Data Collection Business Project |  | FDV - Filip De Ville | [14 empty] | 497 |  |  | Yes | Yes | 2022-06-02 | 2023-06-23 | 265
Work: IMO-R6447-Build&RunTrngProgForAgentsPreMigration | R6447 | 0006447 | 0007514 | ABACUS-Orchestration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT | [16 empty] | 608 |  |  | Yes | Yes | 2022-10-03 | 2023-11-30 | 292
Work: IMO-R6448-Setup dynamic cultural journey for HQ | R6448 | 0006448 | 0007517 | ABACUS-Orchestration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6449-Build and run training program in HQ | R6449 | 0006449 | 0007516 | ABACUS-Orchestration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6450-Orchestrate impl new org & oper model | R6450 | 0006450 | 0007515 | ABACUS-Orchestration | P0 | P3 - Low | Requested | Business Project without IT | Data Collection Business Project | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6451-Dfakto tool | R6451 | 0006451 | 0007500 | ABACUS-Orchestration | P0 | P3 - Low | Requested | Business Project with IT | Data Collection Business with IT |  | FDV - Filip De Ville | [17 empty] | Yes | Yes | 2022-02-07 | 2023-07-03 | 350
Work: IMO-RISK-R6480- Run SAS mensuel partie Retail | R6480 | 0006480 | 0007225 | ABACUS-Integration |  | P0 - Critical | Completed | CR | Data Collection CR | Green | KWO - Katrijn Wolfs | 2020-12-28 | 2021-07-05 | 2020-12-28 | 2021-03-15 | 2.9 |  |  |  | 2.9 | 3.2 |  | 6 |  |  | -0.9 |  |  | Yes | Yes |  |  |  | -75 | 100
Work: IMO-R6484 - Loan data reporting requirements | R6484 | 0006484 | 0007242 | ABACUS-Integration |  | NP | On Hold | Business Project with IT | Data Collection Business with IT | Green | KWO - Katrijn Wolfs | 2021-01-15 |  |  |  | 1.7 | 4 |  |  | 5.7 | [5 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-09 | 3 |  | 29 | [9 empty] | 1.7 | 1.7 | 1.7
Work: ICT-R6597 Tobania Performance Testing | R6597 | 0006597 | 0007284 | ABACUS-Orchestration |  | P1 - High | Completed | IT Project | Data Collection Business with IT | Green | KTO - Koen Tourné | 2021-02-22 | 2022-01-31 |  |  | 17.6 |  |  |  | 17.6 | [5 empty] | -229 |  |  | Yes | Yes |  |  |  |  | 100 | [5 empty] | 4.3 | 3.2 | 10.1 | 4.1 | 13.5 |  | 17.6
Work: IMO-R6926 Pricing & Scoring | R6926 | 0006926 | 0007741 | ABACUS-Integration |  | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6930 Overall migration program | R6930 | 0006930 | 0007743 | ABACUS-Migration |  | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6931 Data Platform-foundation&building blocks | R6931 | 0006931 | 0007744 | ABACUS-Integration |  | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6950 ContentAndCommunicationWebsite | R6950 | 0006950 | 0007750 | ABACUS-Integration |  | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT | [19 empty] | Yes | Yes | 2022-02-07 | 2023-09-29 | 412
Work: IMO-R6953 ABB comm next to Crelan comm system | R6953 | 0006953 | 0007755 | ABACUS-Migration |  | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6954 LightCreditFlow for Brokers | R6954 | 0006954 | 0007756 | ABACUS-Integration |  | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6955 Migrate Procurement Transactions | R6955 | 0006955 | 0007757 | ABACUS-Migration |  | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6956 CommonIntegrLayer-Foundations&Tooling | R6956 | 0006956 | 0007758 | ABACUS-Integration |  | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6957 Design LAN/WAN & Connectivity | R6957 | 0006957 | 0007759 | ABACUS-Integration |  | P0 - Critical | Requested | IT Project | Data Collection IT Project |  | RPE - Ronny Peleman | [14 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6958 Phone migration for HQ | R6958 | 0006958 | 0007760 | ABACUS-Migration |  | P0 - Critical | Requested | Business Project with IT | Data Collection Business with IT | [16 empty] | 4 |  |  | Yes | Yes | 2022-02-07 | 2022-02-07 | 1
Work: IMO-R6972 Erase ABACUS Data&Apps Decommissioning | R6972 | 0006972 | 0007524 | ABACUS-Integration | P0 | P1 - High | Requested | IT Project | Data Collection IT Project |  | ARU - Anita Rubbrecht | [17 empty] | Yes | Yes | 2022-02-07 | 2024-02-02 | 499
Work: IMO-R6973 Execute Performance Test | R6973 | 0006973 | 0007531 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | ARU - Anita Rubbrecht | [14 empty] | 568 |  |  | Yes | Yes | 2023-01-04 | 2023-10-04 | 188
Work: IMO-R6974 RPA capability set up | R6974 | 0006974 | 0007526 | ABACUS-Integration | P0 | P1 - High | Requested | Business Project with IT | Data Collection Business with IT |  | ARU - Anita Rubbrecht | [14 empty] | 484 |  |  | Yes | Yes | 2022-12-05 | 2023-06-06 | 125